## Digital Transformation Tracker
VPS Lakeshore Hospital — Digital Transformation Tracker
Technology & Strategy Office · Updated April 2026 · For Internal Use
# | Initiative | Category | Status | Annual Cost | Timeline / Go-Live | Description | Next Action | Vendor / Options | Owner
LIVE & DEPLOYED
1 | DocuSign | E-Signature & Contracts | Live | — | Apr 2026 ✓ | E-signature platform for HR contracts, vendor agreements, and clinical consent forms. Fully implemented; workflow templates configured and staff trained. | Expand consent templates to surgical admissions. Track turnaround time vs. paper baseline. | DocuSign Inc. | Admin / HR
IN PROGRESS
2 | Voyon Folks — HRMS | HR & Workforce | In Progress | TBD | Launch: Jun 1, 2026 | Cloud HRMS replacing Primato. Covers attendance, leave, payroll, performance, and employee self-service. Training phase underway with HR and dept heads. | Complete dept-level training. Configure payroll parameters. UAT sign-off by mid-May. | Voyon Folks | HR
3 | Website Redesign | Digital Front-End | In Progress | TBD | Go-Live: Jun 30, 2026 | Full public website redesign. Contract signed with Meridian Solutions. Work order this week. 2-month build. Scope: responsive design, SEO, specialty pages, appointment booking. | Issue work order. Kick-off with Meridian. Finalise sitemap and content brief. | Meridian Solutions | Strategy / IT
UNDER EVALUATION
4 | ERP Platform | Finance & Operations | Under Evaluation | ₹90L / yr (each) | Decision: May 2026 | ERP to unify finance (GL, AP, AR), procurement, and inventory. Oracle and SAP proposals both at ₹90L/yr. Oracle aligns with existing RAC infra; SAP offers broader ecosystem. | Reference site visits. Request full TCO models (impl + training). Decision by end-May. | Oracle ERP Cloud SAP S/4HANA | Finance / IT
5 | CRM System | Patient Engagement & Referrals | Under Evaluation | ₹22L / yr (each) | Decision: Jun 2026 | CRM for referral pipeline, patient follow-up, and TPA relationship management. Initial scope: 2 modules. Salesforce and MS Dynamics shortlisted at identical commercial terms. | Pilot demo with BD and marketing teams. Assess Ellider HIS integration effort. | Salesforce Health Cloud Microsoft Dynamics 365 | BD / IT
6 | WhatsApp Business Platform | Patient Communication | Under Evaluation | ₹3–5L / yr (est.) | FY 2026–27 Q1 | Official WhatsApp Business API for appointment reminders, OPD queue alerts, lab report delivery, and post-care follow-ups. Complements existing SMS gateway. | Shortlist BSP (Business Solution Provider). Define message templates for OPD and lab reports. | BSP to be selected | IT / Patient Exp.
7 | ABDM / ABHA Integration | Regulatory & Compliance | Under Evaluation | TBD | FY 2026–27 | Integration with Ayushman Bharat Digital Mission for India's unified health ID. Enables patient health record linkage, consent-based sharing, and NHA compliance. | Confirm ABDM sandbox credentials with Ellider vendor. Assess ABHA enrolment workflow at registration. | NHA / Ellider | IT / Compliance
ROADMAP — FY 2026–27
8 | Payment Gateway | Finance & Patient Exp. | Roadmap | TBD | Q2 FY27 | UPI, card, and wallet payments at OPD billing, pharmacy, and patient portal. Reduces cash handling and settlement lag with insurance/TPA. | Issue RFP after ERP decision (payment module integration dependency). | TBD | Finance / IT
9 | SIEM / Security Ops Centre | Cybersecurity | Roadmap | TBD | Q3 FY27 | Security Information & Event Management with managed SOC. Monitors threats across hospital network. Required for NABH/JCI and DPDP Act compliance. Builds on FortiGate/Cisco infra. | RFP after hospital network audit. Align with DPDP compliance timeline. | TBD | IT / Compliance
10 | HL7/FHIR Interface Engine | Clinical Interoperability | Roadmap | TBD | Q3 FY27 | Interoperability hub for structured clinical data exchange across Ellider HIS, LIS, RIS, PACS, and referral networks. Foundation for ABDM and AI/analytics layer. | Scope requirements post-ERP decision. Ellider vendor to confirm FHIR readiness. | TBD / Ellider | IT / Clinical
11 | Clinical AI — Dx Assist | AI & Advanced Analytics | Roadmap | TBD | FY 2027–28 | AI-assisted diagnostics and risk scoring: radiology image AI, readmission prediction, NLP medical coding. Requires data lake and FHIR interface as upstream dependencies. | Define use-case priority (radiology vs. coding vs. readmission). Dependency: Data Lake + FHIR. | TBD | Clinical / IT

## IT Architecture
VPS Lakeshore — IT Architecture Summary
Architecture Version 1.0.1 · Prepared 28 April 2026 · Technology & Strategy Office
Layer | Domain | Component / System | Status | Notes / Next Steps
FRONT LAYER
Front | Patient Channels | Web Patient Portal (Registration, Reports, Bills) | Existing | Expand appointment booking and bill-pay self-service
Front | Patient Channels | Patient Mobile App (iOS/Android) | Existing | Enhance with push notifications for OPD queue and lab reports
Front | Patient Channels | Doctor App (Rounds, Notes, Orders) | Existing | Integrate with CPOE orders in Ellider
Front | Patient Channels | Staff App (Roster, Tasks, Alerts) | Existing | Connect to Voyon HRMS roster module
Front | Patient Channels | Video Consultation / Telemedicine | Future | Replace current third-party tool with in-house infra change; OPD / follow-up / 2nd opinion
Front | Patient Channels | Remote Patient Monitoring | Future | Wearables & vitals — Holter existing; roadmap for broader RPM
Front | Communication | SMS Gateway | Existing | Active for OPD reminders and lab reports
Front | Communication | WhatsApp Business Platform | Under Evaluation | Official WhatsApp Business API — shortlist BSP; define OPD & lab message templates
Front | Communication | Email / Notifications | Existing | Google Workspace integrated
Front | On-Premises | Self Check-in Kiosks | Future | OPD registration; reduce front-desk queue
Front | On-Premises | Digital Signage / Queue Display | Future | Pharmacy queue display available — extend to OPD
Front | On-Premises | Bedside Entertainment (TV, Feedback, Meal Orders) | Future | Patient satisfaction and upsell opportunity
MIDDLE LAYER
Middle | HIS Core | Ellider HIS — ADT, OPD/IPD, CPOE, Bed & OT Management | Existing | Core HMS. CPOE and OT module to be optimised; API readiness for CRM/ERP integration to be confirmed
Middle | Clinical | Laboratory Information System (LIS) | Existing | Integrated with Ellider; One Dx transition in progress
Middle | Clinical | Radiology Information System (RIS) + PACS | Existing | Imaging live; AI pilot (radiology AI POC done)
Middle | Clinical | Pharmacy System | Existing | Drug formulary revision targeted 15 May; formulary rationalisation in progress
Middle | Clinical | Clinical Decision Support (CDSS) | Existing | Embedded in Ellider; expand coverage
Middle | Clinical | Clinical AI — Dx Assist / Risk Scoring | Future | Trial success on POC; roadmap FY 2027-28 pending Data Lake + FHIR
Middle | Clinical | Nursing Informatics (Care Plans, eMAR) | Existing | Active in Ellider
Middle | Finance & ERP | Billing (IPD / OPD / Pharmacy) | Existing | Ellider-based; TPA claim management and EPM/ECM in scope
Middle | Finance & ERP | General Ledger & Accounts Payable | Existing (fragmented) | ERP platform decision to unify — Oracle or SAP (decision May 2026)
Middle | Finance & ERP | Insurance & TPA Pre-auth & Settlement | Existing | Claim management and EPM to be enhanced
Middle | Finance & ERP | Oracle / SAP ERP Platform | Under Evaluation | Decision by 20 May 2026; Oracle ₹90L/yr confirmed; SAP pricing awaited. Preferred: SAP S/4HANA + Joule
Middle | Finance & ERP | Payment Gateway (UPI / Cards / Wallet) | Future | Issue RFP after ERP decision — payment module dependency
Middle | Finance & ERP | DocuSign — E-Signature & Contracts | Implemented ✓ | Fully live; expand surgical consent templates
Middle | HR & Admin | Primato HRMS (Payroll, Attendance) | Existing — Transitioning | Being replaced by Voyon Folks HRMS; go-live 1 June 2026
Middle | HR & Admin | Voyon Folks HRMS | In Progress | Go-live 1 June 2026; training underway; payroll UAT by mid-May
Middle | HR & Admin | Credentialing System | Existing | Doctor credentialing in Ellider/HR
Middle | Supply Chain | Inventory & Purchase Orders | Future | ERP module will cover consumables and equipment; roadmap post-ERP decision
Middle | Supply Chain | Vendor Management — Contracts & SLAs | Future | ERP vendor management module; Oracle Supplier Portal in scope
Middle | Quality & Compliance | NABH / JCI Tracker | Future | Accreditation management — post ERP/HRMS go-live
Middle | Quality & Compliance | Incident & Safety Reporting | Future | Sentinel events and near-miss; NABH requirement
Middle | Quality & Compliance | DPDP Act Compliance | Future | Consent & data privacy; CIO to incorporate in IT tracker; deadline Q3 FY27
Middle | External & Workflow | Salesforce CRM (Referral & BD) | Under Evaluation | CRM decision May 2026; offer expires 10 May 2026. Shortlisted vs Microsoft Dynamics
Middle | External & Workflow | Microsoft Dynamics 365 CRM | Under Evaluation | Alternative to Salesforce; VPS UAE already on D365; decision May 2026
Middle | External & Workflow | Google Workspace | Existing | Active for email, docs and calendar
Middle | External & Workflow | LinkedIn (Recruitment) | Existing | Recruitment sourcing
Middle | External & Workflow | Adobe Creative | Existing | Marketing and communications use
BACK LAYER
Back | Security | FortiGate Firewall | Existing | Core perimeter security; review after SIEM/SOC RFP
Back | Security | Cisco Core Switch + LAN / VPN | Existing | Network backbone; VPN for remote access
Back | Security | SIEM / Security Operations Centre | Future | Required for NABH/JCI and DPDP Act compliance; RFP after network audit Q3 FY27
Back | Security | Zero Trust / EDR (Endpoint Detection) | Future | Roadmap post-SIEM; endpoint protection across clinical workstations
Back | Compute | Windows IIS Application Servers | Existing | Current app server fleet; containerisation roadmap
Back | Compute | Application Gateway / Load Balancer | Existing | Active
Back | Compute | Container Orchestration (Docker / K8s) | Future | Roadmap for microservices; dependency on ERP SaaS direction
Back | Database | Oracle RAC — 2 Node HA Cluster | Existing | Core database infrastructure; aligns with Oracle ERP path
Back | Database | Standby DB / Disaster Recovery | Existing | Active DR standby
Back | Database | Backup & Scheduled Archiving | Existing | Scheduled; review frequency and offsite copy
Back | Integration | HL7 / FHIR Interface Engine | Existing | Interoperability hub — review FHIR R4 readiness for ABDM
Back | Integration | API Gateway (REST / GraphQL) | Existing | Active; expand for ERP and CRM integrations
Back | Integration | ESB / Message Queue (Event-Driven) | Future | Async integration layer — roadmap post-ERP decision
Back | IoT | Bedside Monitor Integration (ICU Vitals → HIS) | Existing | ICU vitals streaming to Ellider
Back | IoT | Infusion Pump Interface | Future | Smart pump alerts — clinical safety benefit
Back | IoT | RTLS / Asset Tracking (Equipment & Patient) | Future | High-value equipment and patient flow tracking
DATA LAYER
Data | Data Platform | Clinical Data Repository (Unified Patient Record) | Existing | Master patient data — foundation for analytics and ABDM
Data | Data Platform | Master Patient Index (De-duplication & Linking) | Existing | Active; review duplicate rate quarterly
Data | Data Platform | Data Lake / Warehouse (Bronze→Silver→Gold) | Future | Foundation for AI/analytics; roadmap post-ERP go-live
Data | BI & Dashboards | Operational Dashboards (Occupancy, Revenue, TAT) | Available | Active for C-suite; expand department-level coverage
Data | BI & Dashboards | Clinical Quality Indicators (ALOS, Infection, Mortality) | Future | NABH/JCI reporting; roadmap Q3 FY27
Data | BI & Dashboards | Executive Scorecard (C-Suite / Board View) | Available | Active; enhance with AOP initiative tracking overlay
Data | AI & Analytics | Predictive Analytics (Readmission, Demand, No-show) | Future | Requires Data Lake; roadmap FY 2027-28
Data | AI & Analytics | NLP / Medical Coding (ICD-10 Auto-coding) | Existing (pilot) | Pilot successful; scale across clinical departments
Data | AI & Analytics | Image AI (Radiology & Pathology) | Future (POC done) | Radiology AI POC completed; full deployment FY 2027-28
Data | Regulatory | ABDM / ABHA Integration (India Health Data Exchange) | Under Evaluation | Confirm ABDM sandbox credentials with Ellider; ABHA enrolment at registration
Data | Regulatory | Disease Surveillance (IDSP / Notifiable Reporting) | Existing | Statutory reporting active
Data | Regulatory | Birth & Death Registry (Statutory Reporting) | Existing | Statutory reporting active