## Dashboard
AOP EXECUTION DASHBOARD — FY 2026-27 ¦ VPS Lakeshore Hospital
FY 2026-27 ¦ Auto-linked from all sheets ¦ Refresh after actuals entry each month
INITIATIVE STATUS
Total Initiatives |  | Completed |  | In Progress |  | Delayed |  | On Hold | Not Started
50 |  | 1 |  | 1 |  | 0 |  | 0 | 48
FINANCIAL SUMMARY (Rs Lakhs)
Metric | AOP Budget | YTD Actual | Variance (Rs) | Variance % | Status
Revenue from Initiatives | 0 | 0 | 0
Cost of Initiatives | 0 | 0 | 0
Net EBITDA Impact | 0 | 0 | 0
MONTHLY TREND (Rs Lakhs)
Month | Bdg Revenue | Act Revenue | Rev Var | Bdg Cost | Act Cost | Cost Var | Net EBITDA (Bdg) | Net EBITDA (Act)
Apr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
May | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jul | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aug | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oct | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nov | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXCEPTION LOG — Initiatives Flagged
# | Initiative ID | Initiative Name | Status | Ann Budget (Rs) | Ann Actual (Rs) | Variance (Rs) | Var % | Exception Flag
1 | INI-001 | Campaign- Patient experience improvement | Completed | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0
3 | INI-003 | Geriatric ward | Not Started | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | Not Started | 0 | 0 | 0
5 | INI-005 | Patient companion | Not Started | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | Not Started | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | Not Started | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | Not Started | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | Not Started | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | Not Started | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | Not Started | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | Not Started | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | Not Started | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | Not Started | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | Not Started | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | Not Started | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | Not Started | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | Not Started | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | Not Started | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | Not Started | 0 | 0 | 0

## Initiative Register
AOP INITIATIVE REGISTER — FY 2026-27
IDENTIFICATION |  | DESCRIPTION |  |  | OWNERSHIP |  | TIMELINE |  |  | COST |  | SUCCESS CRITERIA |  | FINANCIAL IMPACT |  | STATUS |  | REMARKS
# | Initiative ID | Initiative Name | Function / Dept | Description / Objective | Owner | Designation | Start Month | End Month | Duration (Mths) | Cost Type | Est. Cost (Rs Lkh) | KRA | KPI / Metric | Est. Revenue Impact (Rs Lkh) | Benefit Month | Priority | Status | Remarks / Dependencies
1 | INI-001 | Campaign- Patient experience improvement | Marketing | To enhance overall patient satisfaction by collecting structured feedback, identifying service gaps, and implementing improvement initiatives across departments. | Marketing Head | Manager – Marketing | Mar | Mar | 1 |  | 0 |  |  | 0 |  |  | Completed | No direct financial implication points | final report to receive
2
3 | INI-003 | Geriatric ward | HR & Admin | To establish and operationalize a dedicated geriatric care unit aimed at improving clinical outcomes, patient comfort, and specialized services for elderly patients. | Admin Head | Manager – HR & Administration | [10 empty] | Not Started | Set up a meeting with Kancare a senior care startup (SVP suggestion)
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | HR & Admin | To strengthen clinical capabilities by onboarding specialized doctors and enhancing existing departments to improve service quality and increase patient inflow. | Medical Director | Head – Clinical Services | [10 empty] | Not Started
5 | INI-005 | Patient companion | HR & Admin | To enhance patient experience and continuity of care by providing dedicated patient companions to assist throughout the hospital journey, including admission, in-hospital support, discharge coordination, and periodic follow-up, thereby improving patient satisfaction and retention. | HR Head | Manager | [10 empty] | Not Started | Set up a meeting with Healtheease a Health Startup (SVP suggestion)
6 | INI-006 | Newborn Care Enhancement | Operations | To enhance maternal and neonatal care services by providing comprehensive post-delivery support, including newborn care, mother care, lactation guidance, and structured follow-up programs, thereby improving clinical outcomes and patient satisfaction. | Operations Head | Manager – Operations / Head – Nursing | [10 empty] | Not Started
7 | INI-007 | Digital Patient Acquisition Funnel | Business Development | To strengthen digital patient acquisition by leveraging teleconsultation, digital marketing channels, and conversion optimization strategies to increase OP footfall and IP admissions. | Business Development Head | Manager – Business Development | May | Mar | 11 |  |  |  |  | 0 |  |  | Not Started
8 | INI-008 | Development of KPI for Doctors | HR & Admin | To establish a structured performance management framework for doctors by defining key performance indicators (KPIs) aligned with revenue, clinical outcomes, and patient engagement. | HR Head | Manager – HR | [10 empty] | Not Started
9 | INI-009 | Daycare and Minimaly Invasive Shift | Operations | To improve operational efficiency and reduce average length of stay (ALOS) by promoting daycare procedures and minimally invasive surgical techniques. | Operations Head | Manager – Operations | [10 empty] | Not Started
10 | INI-010 | Consumables standardization model | Supply Chain / Purchase | To optimize cost efficiency by standardizing consumable usage through procedure-wise bundling and reducing wastage across departments. | Purchase Head | Manager – Supply Chain | [10 empty] | Not Started
11 | INI-011 | Collaboration with other Hospitals | Business Development | To expand patient inflow and service capabilities through strategic partnerships and referral networks with other hospitals and specialty centers. | Business Development Head | Manager – Business Development | [10 empty] | Not Started
12 | INI-012 | ANNUAL RATE REVISION POLICY | Finance | Institutionalise a pricing committee meeting every April. Revise all IP rates (room, procedures, OT charges, nursing, clinical charges) by CPI+2% for cash patients. Simultaneously renegotiate TPA/insurance tariffs annually. Prevents multi-year price stagnation — the single biggest structural margin leak in private hospitals. | Finance Head | CFO + CEO | May | May | 1 |  | 0 |  |  | 634.84 | May | High | Not Started | Revenue impact starts from May 2026 onwards- Only the annual impact shown.
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | Finance | Cost out the top 50 procedures by revenue value. For 26% EBITDA, procedure-level contribution must average 58%. Identify all procedures where contribution is below 50%. Revise cash rates. Flag TPA tariff renegotiation list separately. | Finance Head | CFO + Medical Director | May | Jun | 2 |  | 0 |  |  | 9.35 | Jun | High | Not Started
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | Finance | Audit current insurance bills against TPA tariff schedules. Multiple line items (nursing charges, monitoring, clinical charges, physiotherapy, ICU-specific charges) are covered under TPA tariffs but not systematically raised in bills. Fix charge master. Immediate revenue recovery with no new service needed. | Accounts Head | Billing Head | May | May | 1 |  | 0 | [5 empty] | Not Started | Detailes pending | TPA agreements list
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | Business Development | Deploy 6–8 surgeons to run weekly OPD clinics in suburban and district locations (Aluva, Angamaly, Muvattupuzha, Thrippunithura, Kakkanad, Thrissur). Hospital provides space, admin, and branding. Surgeon does one day per week off-campus. Consults convert to admissions at main campus. | Operations Head | COO | May | Oct | 6 |  |  |  |  | 4320 |  | High | Not Started | List of surgical doctors prepared, management to speak to these doctors
16 | INI-016 | CORPORATE HEALTH PROGRAMME | Business Development | Approach top 50 corporates in Kochi (Infopark, Smartcity, BPCL, Cochin Port, FACT, Kochi Metro, KSEB, major hotel chains) for tiered employee health packages: annual health check + OPD benefit + preferential IP rates. Assign dedicated corporate relationship managers. Volume is captive and predictable. | Finance Head | Business Development Head | May | Aug | 4 |  |  |  |  | 354.52 | Aug | High | Not Started | List of corporate received, grouping has to be done
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | Business Development | Partner with major gated communities and apartment complexes in Kochi (Sobha, Prestige, Purva in Kakkanad, Edapally, Thrippunithura) for on-site health camps, resident doctor visits, and emergency response agreements. Low acquisition cost. Drives OPD footfall and diagnostics. | Operations Head | Marketing Head | May | Jul | 3 |  |  |  |  | 0 | May | High | Not Started | General measure already covered in campaign programme
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | Business Development | Kochi airport has direct flights to 12+ Middle East cities. Lakeshore is already on the Kerala Medical Value Travel Society registry and has multilingual (Arabic, Hindi, English, Malayalam) staff and international patient services. Formalise MVT as a growth vertical: empanel with aggregators, assign dedicated MVT coordinator, develop Arabic-language digital content. | Strategy Head | Business Development Head | May | Oct | 6 |  |  |  |  | 614.82 | Oct | High | Not Started
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | Business Development | Map all referring doctors within 50km by specialty and volume. Classify as A/B/C tiers. Assign BD field executives to A-tier (top 100 referrers) with monthly visit cadence. Implement 24-hour discharge summary SOP as a non-negotiable feedback loop for referrers. Track referral volume monthly by doctor. | Finance Head | Business Development Head | May | Aug | 4 | [6 empty] | Medium | Not Started | Data collected from website
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | Business Development | Run monthly CMEs for referring doctors — specialty-specific, with Lakeshore faculty. Rotate across suburban and district locations (Thrissur, Kottayam, Alappuzha, Ernakulam suburbs). Build a registered community of 500+ referring doctors. CMEs generate clinical credibility and direct referral uplift. | Finance Head | Marketing Head | May | Jun | 2 | [6 empty] | Medium | Not Started | CME has to be conducted
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | Finance | Review PMJAY, KASP, CGHS, ECHS, and ESI empanelments. Ensure all eligible procedures — including complex ones like transplant components, cardiac interventions, cancer treatments — are listed. Renegotiate rates for high-volume procedures. At current occupancy levels, scheme patients fill beds that would otherwise be vacant. | Finance Head | Finance Head | May | Jul | 3 |  |  |  |  | 108.39 | Jul | Medium | Not Started
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | Operations | Multi-organ transplant (liver, kidney, pancreas, combined) is Lakeshore's signature clinical programme. Levers: increase deceased donor programme activity, expand living donor evaluation capacity, grow pre- and post-transplant outpatient care, develop dedicated transplant coordinator network. | Operations Head | COO + CEO | May | Jan | 9 |  |  |  |  | 0 | May | High | Not Started
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | Marketing | Lakeshore is recognised for comprehensive cardiac care including interventional cardiology, paediatric cardiology, electrophysiology, structural heart disease, CABG, and LVAD implantation. Growth levers: increase EP lab utilisation, develop structural heart disease programme (TAVR, MitraClip), grow paediatric cardiac surgical volume. | Operations Head | COO + CEO | May | Oct | 6 | [7 empty] | Not Started
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | Business Development | Build a hub-and-spoke oncology model. Hub: Lakeshore for radiation oncology and complex cancer surgery. Spokes: satellite oncology clinics embedded within partner general hospitals and diagnostic centres across Kerala. Spokes drive early detection (oral, breast, cervical, colorectal screening) and funnel diagnosed cases to Lakeshore for surgery and radiation. Chemotherapy delivery at partner sites where appropriate. | Operations Head | COO + CEO | May | Jan | 9 |  |  |  |  | 2126.88 | Feb | High | Not Started
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | Business Development | Lakeshore has India's first digitally integrated orthopaedic OT with guided airflow. Performed first bilateral total hip replacement using ceramic head with metal liner in Asia. Growth levers: fixed-price joint replacement packages, sports medicine programme, fracture care and trauma protocols, robotic-assisted joint replacement. | Operations Head | COO + CEO | May | Aug | 4 |  |  |  |  | 1284.97 |  | High | Not Started
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | Business Development | Organise annual half-marathon or 10K run branded around cardiac health awareness. 3,000–5,000 participants. Entry fee plus sponsorship covers cost. Generates: brand visibility, cardiac health screenings at event (ECG, BP, lipid), OPD follow-ups, cardiologist consultations, and media coverage. | Strategy Head | Business Development Head | Sep | Sep | 1 | Opex - One Time | [6 empty] | Not Started
27 | INI-027 | PREVENTIVE HEALTH + LIVER SCREENING CAMPAIGN | Business Development | Promote preventive healthcare during World Health Day through full body checkups, LFT packages, and fatty liver screening to increase early diagnosis and package conversions.April 19th Liver Day | Marketing Head | Business Development Head | Apr | Apr | 1 | Opex - One Time | 1.12 |  |  | 34.25 | Apr | High | Not Started
28 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | Business Development | Build a sustained health content library across specialties: YouTube, Facebook, Instagram, hospital website. Procedure explainers, doctor Q&As, patient testimonials, disease awareness. Prioritise Lakeshore's clinical differentiators: transplant journeys, cardiac interventions, robotic surgery, cancer care. Malayalam is significantly underserved on health content platforms. | Strategy Head | Business Development Head | Apr | Jun | 3 | Opex - Recurring Monthly |  |  |  | 0 |  | High | Not Started
29 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | Business Development | Run monthly health awareness programmes in schools (adolescent health, vision, nutrition), temples and mosques (senior citizen camps during festivals, post-Ramadan diabetes and cardiac screening), and residential complexes. Low cost. High community trust. Converts to OPD footfall. | Strategy Head | Business Development Head | May | Jun | 2 | [7 empty] | Not Started |  | get the list
30 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | Marketing | Ensure all senior consultants have optimised Google Business profiles, Practo and Doctorundi listings, and detailed hospital website profiles with specialisation, publications, clinical firsts, and patient reviews. Over 60% of new OP patients in urban Kerala search online before choosing a doctor. | Strategy Head | Business Development Head | May | May | 1 | [7 empty] | Not Started | social media capacity building and give a startegy
31 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | Finance | Formal annual tariff revision with all empanelled TPAs and insurers. Most hospital-insurer agreements have not been revised in 2–3 years while costs have risen 12–15%. Engage each TPA separately. Leverage volume and case complexity data. Target: 8–12% rate improvement. | Finance Head | CFO | May | Jul | 3 | [7 empty] | Not Started | As informed by the croproate manager, many are at cash rate itself.
32 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | Operations | Deploy trained financial counsellors at surgical OPD (orthopaedics, cardiac, neurosurgery, oncology, transplant). Role: explain package costs, initiate insurance pre-auth on day of consultation, arrange EMI/loan tie-ups for self-pay patients. Converts deferred decisions to same-week admissions. | Finance Head | CFO | May | Jun | 2 | [7 empty] | Not Started | Currently we have financial counsellors who look into all IP | How many additional finance councellors would be required?
33 | INI-033 | BUILD A SCALED BD ORGANISATION | Business Development | Expand from the current referral-focused BD team to a 27-person full-spectrum function covering: referral development across 3 zones (North, Central, South Kerala); institutional and partnerships (corporate accounts, MVT, satellite clinics, CME); and communications and branding (Arogyam digital platform, PR). Structured under BD Head (Rosh Mohan) reporting to CEO. | Strategy Head | Business Development Head | Apr | Dec | 9 | [7 empty] | Not Started
34 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | Supply Chain / Purchase | Replace branded drugs with equivalent generics/lower-cost brands ensuring same clinical outcome; focus on high-value molecules | Medical Director + Pharmacy Head | Pharmacy Head | Apr | Jun | 3 | [7 empty] | In Progress
35 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | Supply Chain / Purchase | Negotiate higher discounts from manufacturers through volume commitment and MD-level engagement | Purchase Head + MD | Purchase Manager | Apr | May | 2 | [7 empty] | Not Started
36 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | Supply Chain / Purchase | Reduce distributor base and consolidate procurement to extract volume-linked discounts | Purchase Head | Purchase Manager | Apr | Jun | 3 | [7 empty] | Not Started
37 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | Supply Chain / Purchase | Implement competitive tendering and rate contracts for high-value consumables replacing spot purchase | Purchase Head + Medical Director | Purchase Manager | May | Aug | 4 | [7 empty] | Not Started
38 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | Supply Chain / Purchase | Standardise consumable usage across surgeons using procedure-based BOQs and preference cards | Medical Director + OT Head | OT Head | Jun | Sep | 4 | [7 empty] | Not Started
39 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | Supply Chain / Purchase | Reduce inventory holding days and eliminate expiry-related write-offs through stock optimisation | Pharmacy Head + Purchase | Pharmacy Head | Apr | Jun | 3 | [7 empty] | Not Started
40 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | HR & Admin | Reduce linen processing cost and loss through outsourcing optimisation and tracking systems | Admin Head | Housekeeping Head | Apr | Jun | 3 | [7 empty] | Not Started
41 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | Operations | Shift non-critical AMC to third-party vendors and renegotiate OEM contracts for critical equipment | Biomedical Head + Purchase | Biomedical Head | May | Aug | 4 | [7 empty] | Not Started
42 | INI-042 | PAYROLL – NURSING OPTIMISATION | Operations | Align nursing headcount to occupied bed norms through attrition and hiring freeze | COO + Nursing Head | Nursing Head | Apr | Dec | 9 | [7 empty] | Not Started
43 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | Operations | Reduce pharmacy headcount post barcode dispensing and unit-dose system implementation | Pharmacy Head + IT | Pharmacy Head | Apr | Oct | 7 | [7 empty] | Not Started
44 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | HR & Admin | Eliminate manual documentation roles after full EMR implementation in IP wards | COO + IT Head | IT Head | Apr | Mar | 12 | [7 empty] | Not Started
45 | INI-045 | PAYROLL – LAB OPTIMISATION | HR & Admin | Reduce lab headcount via attrition and workflow consolidation without impacting TAT | Lab Head + COO | Lab Head | Apr | Oct | 7 | [7 empty] | Not Started
46 | INI-046 | PAYROLL – OT COST CONTROL | Finance | Eliminate structural overtime through roster optimisation and absenteeism control | HR Head + COO | HR Head | Apr | Jun | 3 | [7 empty] | Not Started
47 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | Admin / HR | Rebid outsourced staffing contracts and rationalise roles for cost efficiency | Admin + HR | Admin Head | May | Aug | 4 | [7 empty] | Not Started
48 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | Engineering | Reduce electricity and DG fuel consumption through scheduling and optimisation | Engineering Head | Engineering Head | Apr | Jun | 3 | [7 empty] | Not Started
49 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | F&B / Admin | Reduce cost per patient meal and food wastage via menu standardisation and controls | F&B Head + Admin | F&B Head | Apr | Jun | 3 | [7 empty] | Not Started
50 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | Finance / Insurance | Reduce insurance claim denials through coding accuracy and pre-auth discipline | Finance + Insurance Team | Finance Head | Apr | Jul | 4 | [7 empty] | Not Started
51 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | Finance / Billing | Recover revenue loss due to incomplete charge capture and billing gaps | Finance + Billing Head | Billing Head | Apr | May | 2 | [7 empty] | Not Started
52 | INI-052 | WORKING CAPITAL – CREDITOR DAYS OPTIMISATION | Finance | Extend creditor days to reduce interest cost and improve cash flow | CFO | CFO | May | Aug | 4 | [7 empty] | Not Started
53 | INI-053 | PROFESSIONAL FEE RATIONALISATION | Finance / Admin | Eliminate redundant retainers and renegotiate professional and subscription contracts | CFO + COO | CFO | Apr | May | 2 | [7 empty] | Not Started
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
TOTALS | [10 empty] | 1.12 |  |  | 9488.02

## Monthly Plan (hidden)
MONTHLY EXECUTION PLAN — Activity Grid (1=Active, 0=Inactive)
Enter 1 in months when the initiative is active. Linked from Initiative Register.
# | Initiative ID | Initiative Name | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Active Months
1 | INI-001 | Campaign- Patient experience improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | INI-003 | Geriatric ward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | INI-005 | Patient companion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | INI-033 | BUILD A SCALED BD ORGANISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | INI-042 | PAYROLL – NURSING OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | INI-045 | PAYROLL – LAB OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | INI-046 | PAYROLL – OT COST CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Cost Plan
COST PLAN — FY 2026-27 ¦ Monthly Budgeted Cost per Initiative (Rs Lakhs)
# | Initiative ID | Initiative Name | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Annual Total
1 | INI-001 | Campaign- Patient experience improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | INI-003 | Geriatric ward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | INI-005 | Patient companion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | INI-033 | BUILD A SCALED BD ORGANISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | INI-042 | PAYROLL – NURSING OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | INI-045 | PAYROLL – LAB OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | INI-046 | PAYROLL – OT COST CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Revenue Impact
REVENUE IMPACT PLAN — FY 2026-27 ¦ Expected Revenue Uplift per Initiative (Rs Lakhs)
# | Initiative ID | Initiative Name | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Annual Total
1 | INI-001 | Campaign- Patient experience improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | INI-003 | Geriatric ward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | INI-005 | Patient companion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | INI-027 | PREVENTIVE HEALTH + LIVER SCREENING CAMPAIGN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | INI-033 | BUILD A SCALED BD ORGANISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | INI-042 | PAYROLL – NURSING OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | INI-045 | PAYROLL – LAB OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | INI-046 | PAYROLL – OT COST CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | INI-052 | WORKING CAPITAL – CREDITOR DAYS OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | INI-053 | PROFESSIONAL FEE RATIONALISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Monthly Actuals
MONTHLY ACTUALS — FY 2026-27 ¦ Enter after each month close (Rs Lakhs)
Section A = Actual Revenue Realised ¦ Section B = Actual Cost Incurred
SECTION A — ACTUAL REVENUE REALISED
# | Initiative ID | Initiative Name | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | YTD Total
1 | INI-001 | Campaign- Patient experience improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | INI-003 | Geriatric ward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | INI-005 | Patient companion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | INI-027 | PREVENTIVE HEALTH + LIVER SCREENING CAMPAIGN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | INI-033 | BUILD A SCALED BD ORGANISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | INI-042 | PAYROLL – NURSING OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | INI-045 | PAYROLL – LAB OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | INI-046 | PAYROLL – OT COST CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | INI-052 | WORKING CAPITAL – CREDITOR DAYS OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | INI-053 | PROFESSIONAL FEE RATIONALISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SECTION B — ACTUAL COST INCURRED
# | Initiative ID | Initiative Name | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | YTD Total
1 | INI-001 | Campaign- Patient experience improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | INI-003 | Geriatric ward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | INI-005 | Patient companion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | INI-033 | BUILD A SCALED BD ORGANISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | INI-042 | PAYROLL – NURSING OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | INI-045 | PAYROLL – LAB OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | INI-046 | PAYROLL – OT COST CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Variance Analysis
VARIANCE ANALYSIS — FY 2026-27 ¦ Budget vs Actual ¦ RED = Exception over threshold
COST VARIANCE (Quarterly + Annual)
# | Initiative ID | Initiative Name | Q1 Bdg | Q1 Act | Q1 Var | Q1 Var% | Q2 Bdg | Q2 Act | Q2 Var | Q2 Var% | Q3 Bdg | Q3 Act | Q3 Var | Q3 Var% | Q4 Bdg | Q4 Act | Q4 Var | Q4 Var% | Ann Bdg | Ann Act | Ann Var | Ann Var% | Exception
1 | INI-001 | Campaign- Patient experience improvement | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
3 | INI-003 | Geriatric ward | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
4 | INI-004 | Appointment of Specialized Doctors and development of existing department | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
5 | INI-005 | Patient companion | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
6 | INI-006 | Newborn Care Enhancement | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
7 | INI-007 | Digital Patient Acquisition Funnel | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
8 | INI-008 | Development of KPI for Doctors | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
9 | INI-009 | Daycare and Minimaly Invasive Shift | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
10 | INI-010 | Consumables standardization model | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
11 | INI-011 | Collaboration with other Hospitals | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
12 | INI-012 | ANNUAL RATE REVISION POLICY | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
13 | INI-013 | PROCEDURE CONTRIBUTION AUDIT AND REPRICING | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
14 | INI-014 | INSURANCE CHARGE CAPTURE — BILL WHAT IS COVERED | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
15 | INI-015 | SATELLITE CLINIC NETWORK — SURGEON-LED OFF-CAMPUS OPDs | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
16 | INI-016 | CORPORATE HEALTH PROGRAMME | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
17 | INI-017 | RESIDENTIAL COLONY AND COMMUNITY HEALTH PROGRAMMES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
18 | INI-018 | INTERNATIONAL MEDICAL VALUE TOURISM — GULF, MALDIVES, BANGLADESH | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
19 | INI-019 | STRUCTURED REFERRAL DOCTOR PROGRAMME | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
20 | INI-020 | CME AND CLINICAL CONNECT PROGRAMME | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
21 | INI-021 | GOVERNMENT SCHEME EMPANELMENT OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
22 | INI-022 | TRANSPLANT CENTRE — VOLUME GROWTH AND DONOR PROGRAMME ACTIVATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
23 | INI-023 | CARDIAC SCIENCES — STRUCTURAL HEART AND ELECTROPHYSIOLOGY VOLUME BUILD | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
24 | INI-024 | ONCOLOGY — EARLY DETECTION, SATELLITE CLINICS AND SURGICAL VOLUME GROWTH | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
25 | INI-025 | ORTHOPAEDICS AND JOINT REPLACEMENT — VOLUME AND PACKAGE PROGRAMME | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
26 | INI-026 | LAKESHORE HEART RUN — ANNUAL CARDIAC HEALTH EVENT | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
27 | INI-028 | DIGITAL CONTENT PLATFORM — MALAYALAM AND ENGLISH | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
28 | INI-029 | COMMUNITY HEALTH CAMPS — SCHOOLS, PLACES OF WORSHIP, RESIDENTIAL AREAS | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
29 | INI-030 | DOCTOR ONLINE REPUTATION AND DIGITAL DISCOVERABILITY | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
30 | INI-031 | TPA AND INSURER TARIFF RENEGOTIATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
31 | INI-032 | FINANCIAL COUNSELLING AND PRE-AUTHORISATION AT SURGICAL OPD | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
32 | INI-033 | BUILD A SCALED BD ORGANISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
33 | INI-034 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
34 | INI-035 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
35 | INI-036 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
36 | INI-037 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
37 | INI-038 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
38 | INI-039 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
39 | INI-040 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
40 | INI-041 | MATERIALS / DRUG COST & CONSUMABLES | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
41 | INI-042 | PAYROLL – NURSING OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
42 | INI-043 | PAYROLL – PHARMACY OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
43 | INI-044 | PAYROLL – ADMIN (PCS) OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
44 | INI-045 | PAYROLL – LAB OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
45 | INI-046 | PAYROLL – OT COST CONTROL | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
46 | INI-047 | PAYROLL – OUTSOURCED CONTRACT OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
47 | INI-048 | OVERHEAD – ENERGY COST OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
48 | INI-049 | OVERHEAD – F&B COST OPTIMISATION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
49 | INI-050 | OVERHEAD – CLAIM DENIAL REDUCTION | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
50 | INI-051 | OVERHEAD – REVENUE LEAKAGE RECOVERY | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0

## KPI Tracker
KPI TRACKER — FY 2026-27 ¦ Monthly Operational & Financial KPIs vs Target
Enter Annual Target in col D. Enter monthly Actuals in cols F-Q. Benchmark in col E.
# | KPI / Metric | Unit | Annual Target | Benchmark | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | YTD Avg
REVENUE & VOLUME
1 | Total Revenue (Rs Lakhs) | Rs Lkh
2 | OP Footfall | Nos
3 | IP Admissions | Nos
4 | ARPOB (Rs) | Rs
5 | ALOS (Days) | Days
6 | Bed Occupancy % | %
7 | OT Utilisation % | %
8 | Surgery Volume | Nos
COST & EFFICIENCY
9 | Employee Cost % of Revenue | %
10 | Drug & Consumable % of Revenue | %
11 | Power Cost (Rs Lakhs) | Rs Lkh
12 | Revenue per Employee (Rs Lkh) | Rs Lkh
13 | Cost per Bed per Day (Rs) | Rs
FINANCIAL PERFORMANCE
14 | EBITDA (Rs Lakhs) | Rs Lkh
15 | EBITDA Margin % | %
16 | Gross Margin % | %
17 | Collection Efficiency % | %
18 | Debtors Days | Days
QUALITY & PATIENT
19 | Patient Satisfaction Score | Score/10
20 | Readmission Rate % | %
21 | Infection Rate % | %
CUSTOM KPIs
22
23
24
25
26

## Initiative Detail Card
INITIATIVE DETAIL CARD — Mini Business Case Template ¦ FY 2026-27
Fill BLUE input cells. Use before entering into Initiative Register.
Initiative Name
Initiative ID | Auto-generated in Register
Function / Department
Owner
Priority | High / Medium / Low
PROBLEM / OPPORTUNITY STATEMENT
What problem does this solve?
What opportunity does this capture?
CURRENT STATE
Current Metric / KPI Value
Source of Data
TARGET STATE
Target KPI Value
Target Timeline
INITIATIVE ACTION PLAN
Key Action Steps
Dependencies / Pre-conditions
Resources Required
FINANCIAL CASE
Cost Type (Opex / Capex)
Estimated Cost (Rs Lakhs)
Expected Revenue Impact (Rs Lakhs)
Payback Period
Net EBITDA Impact (Rs Lakhs)
TIMELINE
Start Month
End Month
Cost Incurrence Period
Benefit Realisation Period
RISKS & MITIGATION
Key Risks
Mitigation Plan
APPROVAL
Prepared By
Reviewed By
Approved By

## Instructions
AOP EXECUTION WORKBOOK — FY 2026-27 ¦ VPS Lakeshore Hospital
Set up ¦ Step up ¦ Scale up — Workbook is intentionally blank. Team fills in initiatives.
HOW TO USE THIS WORKBOOK
STEP | SHEET | ACTION | BY WHOM
1 | Config | Set company name, FY, currency, variance threshold. FY27 Budget targets from Budget_AOP_FY27_UC (WB1). | CFO / Admin
2 | Initiative Register | Functional heads enter their own initiatives. Blank by design. Must cover the EBITDA gap identified in AOP_ReconciliationBridge_FY2627 (WB5). | Functional Heads
3 | Monthly Plan | For each initiative, mark months Active (1) or Inactive (0). Timeline must align with Grey-Zone resource deployment in AOP_AnalyticsEngine_FY2627 (WB2). | Initiative Owner
4 | Cost Plan | Enter budgeted cost (Rs Lakhs) per initiative per month. Totals must reconcile with WB5 Cost_Recon_Summary. | Finance / Owner
5 | Revenue Impact | Enter expected revenue uplift per initiative per month. Totals must reconcile with WB5 Revenue_Recon. | Finance / Owner
6 | Monthly Actuals | Section A = Actual Revenue Realised ¦ Section B = Actual Cost Incurred. Enter after each month close. | Finance
7 | Variance Analysis | Auto-calculated. RED = exception over threshold. Review and escalate per governance protocol. | CFO
8 | KPI Tracker | Track 25+ operational KPIs vs target monthly. Aligned with MPL dept P&L (WB4 / Layer 4). | Operations / Finance
9 | Dashboard | Executive dashboard — scorecards, financial summary, monthly trend, exception log. Board-ready. | CFO / Board
10 | Initiative Detail Card | Mini business case + Progress Card per initiative. Row # selector loads live planned vs actual data. | All Initiative Owners
COLOUR CODING LEGEND
BLUE TEXT = Input cells — fill these in
BLACK TEXT = Formula cells — do not overwrite
GREEN TEXT = Values linked from other sheets
RED BACKGROUND = Exception / adverse variance over threshold
YELLOW BACKGROUND = Input required / needs attention

## Config
WORKBOOK CONFIGURATION
Parameter | Value | Notes
Company Name | VPS Lakeshore | Enter organisation name
Financial Year | FY 2026-27 | e.g. FY 2026-27
Currency | INR | INR / USD / AED etc.
Currency Unit | Lakhs | Lakhs / Crores / Thousands
Variance Alert Threshold (%) | 10 | % over budget that triggers RED exception flag
AOP Prepared By
AOP Approved By
Date of Preparation |  | dd-mmm-yyyy
FUNCTIONAL DEPARTMENTS
Operations
HR & Admin
Finance
IT / Systems
Business Development
Marketing
Clinical Services
Supply Chain / Purchase
Quality & Compliance