## ATR pending
Sl. No | Observation | Audit period | Responsible person | Management response | Status | Action planned | timeline
| Sep 2025-Dec 2025 | Sep 2025-Dec 2025
1 | Reconciliation of Revenue Between Two Software Used and its impact in GST Reporting | Sep 2025-Dec 2025 | S.M Finance,IT | Reconciliation at finance level currently not feasible due to some limitations. Issue requires resolution at the IT/ System configuration level. | Working | IT department was directed for a detailed investigation and resolution. | 2026-04-15
2 | Inadequate Controls Over Settlement Closure Leading to Discrepancies in Ageing Report | Sep 2025-Dec 2025 | S.M Finance, IT | Errors of unchecking of ‘Finished’ is corrected. Will implement periodical review also. Issues requires resolution from IT Level already escalated | Working | IT department was directed to set an automated system for ‘Finished’ status when the amount matches the bill amount to eliminate manual errors. Additionally, periodic review mechanisms will be established to monitor settlement closures and ensure data accuracy. | 2026-04-15
3 | Control Gaps in Suspense and IP Cash Temporary Accounts | Sep 2025-Dec 2025 | S.M Finance | Appropriate controls will be strengthened to ensure timely reco & and clearance | Working | Finance department was directed to reconcile the "Suspense account" and analyse the root cause and transfer the balance to appropriate Income . Also directed for detailed reconciliation of "IP cash control account" which should be categorised as receivable | 2026-04-30
4 | Long-Outstanding Unreconciled/ Unsettled Items in Bank Reconciliation Statement | Sep 2025-Dec 2025 | S.M Finance | Details regarding to some unsettled amounts received during January/ February 2026. Company is trying to collect the details as much as possible. | Working | Finance department was directed to ensure monthly closure of banks. Daily receipts and payments must be accounted and for the un reconciled items ,regular follow-up actions to be initiated from finance. | 2026-04-30
5 | Non-Adherence to Monthly Bank Reconciliation Process | Oct 2024-Dec-2024 | S.M Finance | Monthly BRS will be prepared for all banks and a formal signoff be ensured . | Working | Internal auditor was directed to Follow-up monthly documentation of BRS. | 2026-04-07
6 | Variance between MIS & Trial Balance due to subsequent adjustments/ backdated entries | Sep 2025-Dec 2025 | S.M Finance | Monthly closure process will be implemented to avoid discrepancies in future | Working | Finance department was directed to strictly implement monthly closure activities | 2026-04-07
7 | B2C Supplies reported as B2B supplies in GST returns | Sep 2025-Dec 2025 | S.M Finance |  | Closed | Closed | Closed
8 | B2C Supplies reported as Exempted supplies in GST returns | Sep 2025-Dec 2025 | S.M Finance |  | Closed | Closed | Closed
9 | Errors in TDS Payment Due to Duplicate Accounting Entry | Sep 2025-Dec 2025 | S.M Finance |  | Closed | Closed | Closed
10 | Improvements Required for System Restriction in PO Approval Workflow | Sep 2025-Dec 2025 | Chandrasekhar (CIO) |  | Closed | Closed | Closed
11 | Inadequate Role-Based Access Controls in Mediware | Sep 2025-Dec 2025 | Chandrasekhar (CIO) |  | Closed | Closed | Closed
12 | Incorrect GST rates application in billing | Sep 2025-Dec 2025 | Mr.Sreesan (Purchase), Jayasoorian , SM Finance | Updation will be done along with GRN creation and all items will be covered by June 26 | Working | Internal auditor was directed to check some sample cases. | 2026-04-07
13 | Improper Availment of ITC and Weak Reconciliation Controls | Sep 2025-Dec 2025 | S.M Finance, IT | ERP does not provide a report for GST return filing. Reco between ITC available in books and ITC appearing in GSTR-2B currently not being done. Additional staffing planned. | Working | IT department was directed to generate GST reports enabling reconciliations. | 2026-04-30
April 2025-Sep 2025
1 | Consumption entry not posted for inventories | April 2025-Sep 2025 | Mr.Jayasoorian, Manager-Bio Medical Eng. | Department supervisors should perform periodic reconciliations between ERP records and physical stock to identify and correct deviations promptly | Working | Store manager was directed to do monthly reconciliation of system stock and physical stock, correct the deviations and also submit report to CFO. | 2026-04-30
2 | Use of the manual indent process in the procurement of capital goods | April 2025-Sep 2025 | Mr.Sreesan (Purchase),IT | We have reviewed the observation and agreed with the recommendation. The hospital has decided to implement the Asset Management Software with an integrated workflow for capital equipment indenting, approval, and notification. This will ensure a standardized and transparent process across departments. Implementation planning is in progress in coordination with the IT Department. | Working | IT department was directed to complete implementation of AMS and it will eliminate manual indent process. | 2026-04-15
3 | Return of consignment stock items not recorded properly | April 2025-Sep 2025 | Mr. Jayasoorian Manager-stores | We will immediately implement the process of updating consignment stock returns to vendors in the stock register maintained at the general store. Pending entries will be corrected immediately, and designated personnel will monitor compliance. Additionally, staff training and monthly reconciliations between physical stock and system records will be conducted to maintain accuracy and strengthen internal controls. | Working | Store manager was directed to submit a monthly report of consignment stock to CFO after physical verification and deviations identified to be corrected immediately. | 2026-04-15
4 | Non-Compliance with Standard Operating Procedures (SOP) | April 2025-Sep 2025 | Assistant manager-CSSD | Adherence to the SOP for ultrasonic machine use in instrument washing has begun, and documentation is being recorded in the Receiving and Washing Register. Water changes will also be documented in the same register. | Closed | Internal auditor was directed to check the registers kept to record water changes-Check and close | 2026-04-07
5 | Non-Compliance with SOP on Patient Advance Refund Processing | April 2025-Sep 2025 | Ms.Lijia-Manager,Billing,IT | As per the SOP, cash refunds to patients are permitted only for amounts below ₹10,000. However, in the case of foreign patients, refunds exceeding ₹10,000 may be made in cash in multiples of ₹9,500, as bank transfers are not possible for such cases and in the case of domestic patients, refunds below ₹10,000 may be made in cash, while refunds exceeding ₹10,000 must be processed only through bank transfer or cheque. But unfortunately, In the case of patient ID 642052, an amount of ₹18,900 was mistakenly refunded in cash by Billing Staff, instead of following the prescribed SOP. To prevent such errors in the future, strict instructions have been given to all billing staff to adhere to the SOP without exception. | Working | It department was directed to Implement IT control blocking payment of mor than Rs.10,000 in cash, also check whether the existing control are working properly i.e.. Receipts of more than Rs. 200,000 in cash. | 2026-04-15
6 | Duplication in Vendor Master | April 2025-Sep 2025 | Mr.Sreesan (Purchase), Accounts | Vendor names with slight variations are done in the vendor master as those vendors are having different registered addresses. The duplicate payment said by the audit can be due to the wrong manual linking made at FA. The vendor’s name in this case are identical which we are unable to change. To track the duplicate PAN/GSTN may be activated in the ELLIDER software. | Working | Purchase department was directed to update the vendor master considering active vendors(having transactions for the last 12 months). Filling PAN,GSTIN,Bank details , MSME status are mandatory. Accounts/Finance department was directed to make payments based on GSTIN/PAN +Name basis | 2026-04-30
| Jan25-March25 | Jan25-March25
1 | Unrestricted Rate Edit Functionality in Hospital Management Information System | Jan25-March25 | Ms.Lijia-Manager,Billing | OP editing is not required, and we will take the necessary initiative to disable OP editing to strengthen controls. With respect to IP billing, editing rights are currently available to two users, as this is sometimes essential for processing insurance claims and package-related adjustments. We will ensure that this access is monitored, and any edits are properly authorized and documented. | Working | Internal auditor was directed to check whether OP editing rights are withdrawn or not also check IP billing editing rights, RBAC | 2026-04-07
2 | Discrepancies in Scheme tariff rate master with Memorandum of Understandings | Jan25-March25 | Ms.Lijia-Manager,Billing | We will ensure that the tariff in the system is updated to match the MoU rates for Star Health and Allied Insurance at the earliest. Additionally, we are in the process of creating and implementing a package structure for Star Health, which will be updated in the system soon. It is also noted that certain procedures were added to the system after the MoU was signed. If patients have availed such services, they were billed at the open tariff rate as no agreed rate existed in the MoU. Steps are being taken to address these gaps and ensure consistency in future billing | Working | Internal auditor was directed to check edit log and user access rights. Also check for deviations in tariff rates. | 2026-04-07
3 | Manual adjustment of room days in HMIS Billing | Jan25-March25 | Ms.Lijia-Manager,Billing | The editing rights in IP billing are required in specific cases, such as for waiving off charges related to short-stay patients, where applying full-day charges would not be appropriate. Additionally, when a room category changes during a patient’s stay, we charge for the full day as per hospital policy. These edits help ensure accurate and fair billing aligned with operational requirements. | Working | Internal auditor was directed to check edit log and user access rights. | 2026-04-07
4 | Nursing charges not excluded in room rent occupied by bystanders | Jan25-March25 | Ms.Lijia-Manager,Billing & IT | The issue of manual adjustments for room occupancy by bystanders needs to be addressed through a system enhancement. This has been escalated to the IT department for configuring automatic calculation of charges for rooms occupied by bystanders to ensure accuracy and consistency in billing. | Working | IT department was directed to configure automatic calculation of room charges for rooms occupied by bystanders. | 2026-04-15
5 | No reconciliation between revenue and collections on a periodical basis | Jan25-March25 | SM. Finance, IT | At present, while both reports are available, the reconciliation process is hindered due to duplicate bill numbers appearing in the data dump. This issue arises because the bill number prefixes (used to differentiate between billing series for pharmacy, laboratory, IP discharges, Calicut unit, etc.) are trimmed off during export to Excel, resulting in duplication of bill numbers across different billing streams. | Working | Billing prefix gets trimmed off during export to excel. IT department was directed to resolve this issue. Finance department was directed to do the periodic reconciliation of both the reports. | 2026-04-15
6 | Delay in attendance regularisation request by employees | Jan25-March25 | Manager, HR | The attendance regularisation done after the payroll processing, will be against the request mail received from HOD. The corresponding arrears, if any, will be processed and disbursed in the following month’s payroll. That is the reason it shows regularisation after 30- 35 days. | Working | Hr Department was directed to issue a circular on the issue, demanding regularisation request on time from all the staffs. Also request after the salary period will be | 2026-04-07
7 | Improper punch in and punch outs | Jan25-March25 | IT | Many at times, software is not catching the face detection properly. Whereas when we check manually it was found that the person is present at his/her department on time. | Working | Hr Department may decide the need for retina based punch in and punch out. Issue a circular on all existing cases to all the staffs | 2026-04-07
8 | Approvals granted for Privilege leave exceeding 3 days without prior 3-day notice | Jan25-March25 | Manager, HR | Many people used to take PL against Sick (sick leave is only for 12 days) which they won’t be able to request in advance. However, we will take a track to rectify this anomaly or misuse of the policy | Working | HR Department was directed to issue a circular outlining the updated terms and conditions for the interchangeability of Privilege Leave and Sick Leave. The circular will also include necessary safeguards and monitoring mechanisms to prevent misuse and ensure appropriate compliance with the leave policy. | 2026-04-07
9 | Discrepancies in MSME Identification and Payments | Jan25-March25 | SM. Finance, IT, Purchase | We are committed to resolving these gaps through system improvements and stricter enforcement of the SOP and will continue to follow up with IT and department heads to expedite these corrective measures. | Working | IT department was directed to produce a bills due report in this case also MSME updation and credit period has to be set in system by purchase team | 2026-04-07
10 | Non- compliance with Board – Approved salary increments limits | Jan25-March25 | Manager, HR | The salary increments exceeding the 10% limit authorized by the Board of Directors will be placed before the Board for ratification in the upcoming meeting. | Closed | Closed | Closed
12 | Risk in user access rights in Primato | Jan25-March25 | Manager, HR | Many staff have the privilege (automatically done by the system) to have first level approval which was explained to Auditors. The second level approval comes to HOD and then only leaves will be accepted by the system. This will be corrected by making it as Direct Approval. | Working | Internal auditor was directed to check approval Metrix and its working . | 2026-04-07
13 | Non clearance of resigned employees from F&B dues | Jan25-March25 | Manager, F&B | The mentioned employees have been inactivated. We will update the resigned staff list in the billing software accordingly | Working | Internal auditor was directed to check random cases and close the point | 2026-04-07
| Oct 2024-Dec-2024 | Oct 2024-Dec-2024
1 | Underbilling of ED/ Nursing charges at the Emergency Department | Oct 2024-Dec-2024 | Billing, Emergency department | We are admitting the omission in charging the Extra Rs.100/hour of patients occupied more than 4 hrs in ER in the mentioned cases. From 11.02.2025 onwards we have given strict instructions to ER Billing staff to charge, if the patient occupancy exceeds 4 hours in ER, an ED charge of Rs.100/ hours must be charged without any fail. In case of any fault from the billing staff regarding the same the concerned staff in time is responsible to pay the due amount. | Working | Internal auditor was directed to check random cases and close the point | 2026-04-07
2 | Deficiencies in the billing procedures at the emergency department | Oct 2024-Dec-2024 | Billing, Emergency department | We have not observed any system deficiencies in this scenario. Previously, we had configured causality schemes valid for EOD. As per the request, we have now updated this configuration to 48 hrs. | Closed | Closed | Closed
3 | Lack of ROI / Payback Analysis for Major Asset Purchases | Oct 2024-Dec-2024 | Mr.Sreesan (Purchase) | Plan of ROI is not practical in those cases when the purchased equipment is not directly involved with the patient care/therapy, eg: Patient Cot, Patient positioners, OT Tables, etc. Also, in the case of major purchases such as OT Robot, the ROI was not taken, because those machineries were essential to be procured to compete with the similar institutions in our surroundings | Working | Purchase team was directed to fill the ROI on bio medical equipments after the discussion with bio medical department. | 2026-04-15
4 | Lack of Controlled Access and Inadequate Inventory Tracking in OT Store | Oct 2024-Dec-2024 | Mr.Jayasoorian (Stores) | The work for the installation of counter at the entrances to restrict the unauthorised entry and also to restrict the unauthorized item distribution is started. | Closed | Closed | Closed
5 | Absence of System Defined Reorder Levels | Oct 2024-Dec-2024 | Mr.Jayasoorian (Stores) | We submitted a request to implement the ROL (Reorder Level) system in the General Store. However, we have over seven thousand items that have no transactions or stock, which could cause errors in the ROL system. We have already submitted a request to IT department to block these items in order to ensure the proper functioning of the ROL system. Once this is done, we will proceed with operating the ROL system. We will assess the feasibility of generating exception reports directly within the system. | Working | Internal auditor was directed to check the status of ROL updation in system. | 2026-04-07
6 | Issue to outlets against old intends | Oct 2024-Dec-2024 | Mr.Jayasoorian (Stores) | In most cases, staff members are requesting bulk quantities, but we will issue a minimum quantity as per the guidelines, will request to IT to cancel the excess indent. | Closed | Closed | Closed
7 | Erroneous consumption entry posted for capital assets | Oct 2024-Dec-2024 | Mr.Jayasoorian (Stores), Mr.Sreesan(Purchase) | When the item master is being prepared by the purchasing team, they should correctly select whether the item is an asset, consumable, or medicine. If they make the correct selection, this will prevent any issues from arising. The Purchase department has communicated with the IT department regarding the system default in the item master that needs to be corrected. They have also requested to track how the default was generated. | Working | Purchase department was directed to clean item master. Rectify wrong classifications | 2026-04-20
| April 2024-Sep-2024 | April 2024-Sep-2024
1 | Non-Settlement of Patient Payables (i.e. Amount due from patients) in ERP Post Issuance of IP Receipt Voucher to the Patients | April 2024-Sep-2024 | Ms.Lijia-Manager,Billing | Insurance reimbursement is applicable only when the patient settles the invoice amount. In the present cases also an IP receipt voucher is issued for the patient from hospital to reimburse and the payment will be cleared by M/s.Aldun to our hospital as per MOU terms. There are increasing numbers of the RAC cases where we are not having a tie up with the insurance companies. If we do not follow this practice we will lose the reimbursement business .We can consider bringing changes to this practice at the time of renewal of MOU as recommended. | Closed | Closed | Closed
2 | Delay in settlement of amounts by M/s. Trust Bridge Technology Private Limited (“ALDUN”) | April 2024-Sep-2024 | Receivables-Accounts | As per our records the amount due from M/s. Aldun, for both RAC and ID cases are Rs. 72.14 Lakhs. We are following up for the payment and the reasons for the delay. We have contacted senior the officials of M/s. Aldun and got the assurance that the payment will be released within a week’s time. | Closed | Closed | Closed
3 | Review of Commission/ Fee Payment to M/s. Trust Bridge Technology Private Limited (“ALDUN”) | April 2024-Sep-2024 | SM. Finance | We have entered into an MOU with M/s. Aldun and as per MOU we have to pay Rs 500/- as charges even for cases less than Rs 5000/-. As recommended here, we will negotiate for the lesser charges at the time of next renewal for cases less than Rs 5000/-. | Working | Internal auditor was directed to check below 5000 cases and identify new rates. | 2026-04-07
4 | Improper follow up of Receivables from Bond / MACT Cases | April 2024-Sep-2024 | Ms.Lijia-Manager,Billing | At present the documentation and safe custody of the bonds are with the Billing Department. The bonds are being collected at the time of discharge of the patients. A revised updated report on Bonds after correcting the deficiencies will be submitted by AM billing shortly. | Working | Billing Manager was asked to update the cases and reconcile the balance along with status . Reports are to be submitted to CFO. Also receivable teams was also directed to do the reconciliation of bond cases. | 2026-04-07
5 | Errors in selecting Cash and Credit scheme while Billing | April 2024-Sep-2024 | Ms.Lijia-Manager,Billing |  | Working | Internal auditor was asked to check sample cases and close the point | 2026-04-09
6 | Discount Rates are Different from Rate Quoted in MOU with Corporate Debtors. | April 2024-Sep-2024 | Ms.Lijia-Manager,Billing, IT | Manual interference to set discount rates not followed any more. Usually, package rates and discounts are set with the support of IT team. We will definitely take necessary steps to avoid these types of deviations while entering the rates in the tariff master in future. | Working | IT department was directed to set discount fields also in modules. | 2026-04-30
7 | Deviation in Accounting of Recovery of Patient Dues from Employee's Salary | April 2024-Sep-2024 | Receivables-Accounts ,Ms.Lijia-Manager,Billing | The point which is mentioned in Anx-8 is corrected by passing necessary entries in HIS recently. The point which is mentioned in Anx-8 is corrected by passing necessary entries in HIS recently. Above 3 years cases, which is mentioned in the Anx-9 will be checked with the pay slips in coordination with HR department. These data can be shared at the earliest. | Working | Internal auditor was directed to check the cases mentioned in report are cleared or not also directed to heck Above 3 year cases mentioned in audit report with HR team. | 2026-04-15
8 | Control Weakness in Cash Depositing Practice | April 2024-Sep-2024 | Accounts, Billing | The custody of the locker which is kept in the IP billing is under the control of Accounts department. The locker facility in IP billing is the deposit point of daily cash collection of all the IP billing staff. There is a cash register kept near the locker for recording daily collection by each user. The cross verification of cash register with cash in locker is done by the accounts Staff and tallied on a daily basis and prompt action is taken for any deviations. We have instructed the IP billing manager to oversee this process on a daily basis. | Working | Billing manager was directed to ensure Senior officer in the shift sign-off the settlement and same should be in practice for F&B also. | 2026-04-07
9 | Delay in Posting Entries in case of AMC's | April 2024-Sep-2024 | Mr. Sreesan (Purchase)/Finance, Bio-medical | We have intimated the user department, Bio –medical engineering, to forward the invoice immediately to the finance department for accounting. Also, we are taking steps to remind the User departments to submit the invoice of the CMC-AMC on a timely manner against the advance payment | Closed | Bio Medical department was directed to submit all the bills on time also not to process any AMC before proforma. | 2026-04-15
| Jan 2024-March 2024 | Jan 2024-March 2024
1 | Discrepancy in billing / consumption of Buffer Stock and Crash cart stock | Jan 2024-March 2024 | Mr. Jacob Mathew Billing/Pharmacy/Medical store | The process is corrected and as per revised practice, the details of items used for patients from buffer stock/ crash cart are given to ward secretaries and those items are billed to patients. | Closed | Closed | Closed
2 | Issues in billing of Oncology Medicine | Jan 2024-March 2024 | Ms.Lijia-Manager,Billing, IT | As per our hospital practice, we do add hospital mark-up on oncology medicines as mentioned by the audit above, whereas policy documentation is yet not maintained by us. Most of the items sold at a margin less than 20% are price-controlled items. In certain cases covered by insurance, the mark can be more than 20% also. We shall ensure documentation in the effect soon. | Working | Internal auditor was directed to check whether any policy documentation is available in this regard. | 2026-04-07
3 | Under-utilization of credit period | Jan 2024-March 2024 | SM finance/Purchase, IT | The company may explore the feasibility of incorporating a payment blocking system for invoices not yet due, considering the credit period and cash discount benefits. | Working | IT department was directed to provide bills due report and establish a payment blocking system on bills not yet due. | 2026-04-20
4 | Review of Fixed Asset Register | Jan 2024-March 2024 | SM finance, IT | Asset register is being maintained under new asset management software. | Working | IT department was directed to complete the implementation of AMS asap. | 2026-04-15
5 | Long outstanding creditors for capital goods | Jan 2024-March 2024 | SM finance, Purchase, IT | Periodical review of vendors will be performed and these amounts are not seen payable and proposed for write back. | Working | IT department was directed to provide bills due report . Finance department was directed to reconcile the existing long outstanding list and recommended to settle or write back accordingly. | 2026-04-20
| Apr-24-Dec-24 (From the ATR pending list of Q4 24-25 report) | Jan 2024-March 2024
1 | Long pending advance payments | Jan 2024-March 2024 | Finance/Accounts | Payments made towards expenses, where the corresponding bills have not been submitted by the concerned departments. In view of the prolonged period without movement, it is advised to consider writing off these balances after completing appropriate internal checks and obtaining necessary approvals | Working | Finance department was directed to write -off the long outstanding advances. | 2026-04-15
2 | Vendor master data GST numbers and Mobile numbers not updated, no designated column for entering PAN, bank account number, IFSC code, MSME registration details, etc. | Jan 2024-March 2024 | SM finance, Purchase |  | Working | Purchase department was directed to update the vendor master considering active vendors(having transactions for the last 12 months). Filling PAN,GSTIN,Bank details , MSME status are mandatory. Accounts department was directed to make payments based on GST. | 2026-04-30
3 | Date of PO after bill date | Jan 2024-March 2024 | Mr.Sreesan (Purchase) | Most of these cases happened when the purchase order amendments were done due to the reasons such as price variation (rate/mrp). In such cases when the original PO was amended, a new PO number is being created. Therefore, these date variations are evident. However, we shall take up this with IT department to resolve the issue as appropriate so that similar observation can be avoided in future. | Working | Internal auditor was directed to check some samples cases of PO and check the need for IT controls | 2026-04-15
4 | Suspense Account Reconciliation pending | Jan 2024-March 2024 | SM finance | We acknowledge the audit observation regarding the balance in the Suspense Account. The credit balance of ₹153.25 lakhs as of 31st March 2025 represents an accumulation over the past three years. This amount primarily consists of unidentified bank transfers from customers, where no claims have been received, as well as receipts from insurance companies and ECHS that are yet to be identified and settled against the corresponding bills | Working | Finance department was directed to reconcile the balances, identify the root cause and transfer it to appropriate income heads. | 2026-04-15
5 | Inappropriate Categorisation in stock reports | Jan 2024-March 2024 | Mr. Jayasoorian (Stores)Mr.Sreesan (Purchase) | Working on that | Working | Purchase department was directed to clean item master. Rectify wrong classifications. | 2026-04-15
6 | Staff benefits and discount availment after resignation | Jan 2024-March 2024 | Ms.Lijia-Manager,Billing, IT | Will recheck with IT and ensure strict compliance in erasing out the left employees and their dependents from the system. | Closed | Closed | Closed

## Sheet2 (hidden)
24-25 Q4
1 | Effectiveness of Billing system and revenue assurance
o Scheme wise billing review
o Billing process review
o Rate list updation review
o Cash control in Lab, Pharmacy, Endoscopy, Oncology, Fastrack, Executive
2 | Human Resource
o Attendance capturing
o Data Integrity
3 | Food and Beverages
o Billing process
o Cash verification
o Procurement to payment cycle
4 | Departmental verification
o Joint replacement and Sports medicine
5 | Vendor Payments
o Compliance with MSMED Act, 2006
o Validation of reporting mechanism
6 | Operating Expense
o Security expense
o Housekeeping and Laundry
o Advertising, marketing and business development
o Power and fuel
o Rent
7 | Other Matters
o Physical stock counting of OT and Cathlab
8 | Follow up of Internal Audit Observations during the FY 2023-24

## Internal audit points (hidden)
Sl. No | Observation | Status
Oct 2025-Dec 2025
1 | Incorrect GST rates application in billing | Working
2 | B2C Supplies reported as B2B supplies in GST returns | Corrected
3 | B2C Supplies reported as Exempted supplies in GST returns | Corrected
4 | Improper Availment of ITC and Weak Reconciliation Controls | Working
5 | Errors in TDS Payment Due to Duplicate Accounting Entry | Corrected
6 | Reconciliation of Revenue Between Two Software Used and its impact in GST Reporting | Working
7 | Improvements Required for System Restriction in PO Approval Workflow | Corrected
8 | Inadequate Role-Based Access Controls in Mediware | Corrected
9 | Inadequate Controls Over Settlement Closure Leading to Discrepancies in Ageing Report | Working
10 | Control Gaps in Suspense and IP Cash Temporary Accounts | Working
11 | Long-Outstanding Advance from Patients | Working
12 | Long-Outstanding Unreconciled/ Unsettled Items in Bank Reconciliation Statement | Working
13 | Non-Adherence to Monthly Bank Reconciliation Process | Working
14 | Variance between MIS & Trial Balance due to subsequent adjustments/ backdated entries | Working
April 2025-Sep 2025
1 | Consumption entry not posted for inventories | Working
2 | Use of the manual intent process in the procurement of capital goods | Pending follow-up
3 | Non-insistence of site supervision across various hospital works despite being stipulated in work orders | Pending follow-up
4 | Work permits were not issued or renewed timely and appropriately, leading to unauthorized work and non-compliance with safety protocols | Pending follow-up
5 | Penalties for delay in work orders were not imposed despite contract timelines being exceeded | Pending follow-up
6 | Inadequate Tracking and Documentation of Reused Balloons in Cath lab | Pending follow-up
7 | Return of consignment stock items not recorded properly | Pending follow-up
8 | Non-Compliance with Standard Operating Procedures (SOP) | Pending follow-up
9 | Non-Compliance with SOP on Patient Advance Refund Processing | Pending follow-up
10 | Duplication in Vendor Master | Pending follow-up
11 | Inadequate Employee Tracking in Billing Discount Application | Pending follow-up
Jan25-March25
1 | Unrestricted Rate Edit Functionality in Hospital Management Information System | Pending follow-up
2 | Discrepancies in Scheme tariff rate master with Memorandum of Understandings | Pending follow-up
3 | Manual adjustment of room days in HMIS Billing | Pending follow-up
4 | Nursing charges not excluded in room rent occupied by bystanders | Pending follow-up
5 | No reconciliation between revenue and collections on a periodical basis | Pending follow-up
6 | Delay in attendance regularisation request by employees | Pending follow-up
7 | Improper punch in and punch outs | Pending follow-up
8 | Approvals granted for Privilege leave exceeding 3 days without prior 3-day notice | Pending follow-up
9 | Discrepancies in MSME Identification and Payments | Pending follow-up
10 | Integration of Billing software with Pinelabs | Pending follow-up
11 | Non- compliance with Board – Approved salary increments limits | Pending follow-up
12 | Inconsistencies in Staff Discount Rates | Pending follow-up
13 | Risk in user access rights in Primato | Pending follow-up
14 | Non clearance of resigned employees from F&B dues | Pending follow-up
Oct 2024-Dec-2024
1 | Underbilling of ED/ Nursing charges at the Emergency Department | Pending follow-up
2 | Deficiencies in the billing procedures at the emergency department | Pending follow-up
3 | Lack of ROI / Payback Analysis for Major Asset Purchases | Pending follow-up
4 | Delay in Posting Entries in case of AMC's | Pending follow-up
5 | Lack of Controlled Access and Inadequate Inventory Tracking in OT Store | Pending follow-up
6 | Absence of System Defined Reorder Levels | Pending follow-up
7 | Issue to outlets against old intends | Pending follow-up
8 | Erroneous consumption entry posted for capital assets | Pending follow-up
9 | Issues noted in AMC / CMC contract maintenance and its compliance | Pending follow-up
April 2024-Sep-2024
1 | Non-Settlement of Patient Payables (i.e. Amount due from patients) in ERP Post Issuance of IP Receipt Voucher to the Patients | Pending follow-up
2 | Delay in settlement of amounts by M/s. Trust Bridge Technology Private Limited (“ALDUN”) | Pending follow-up
3 | Review of Commission/ Fee Payment to M/s. Trust Bridge Technology Private Limited (“ALDUN”) | Pending follow-up
4 | Improper follow up of Receivables from Bond / MACT Cases | Pending follow-up
5 | Errors in selecting Cash and Credit scheme while Billing | Pending follow-up
6 | Discount Rates are Different from Rate Quoted in MOU with Corporate Debtors | Pending follow-up
7 | Deviation in Accounting of Recovery of Patient Dues from Employee's Salary | Pending follow-up
8 | Control Weakness in Cash Depositing Practice | Pending follow-up
9 | Delay in Posting Entries in case of AMC's | Pending follow-up
Jan 2024-March 2024
1 | System deficiency in Purchase posting during conversion of temporary GRN to original GRN | Pending follow-up
2 | Discrepancy in billing / consumption of Buffer Stock and Crash cart stock | Pending follow-up
3 | Issues in billing of Oncology Medicine | Pending in 24-25 Q4 follow-up
4 | Lack of Committee Approval for Purchase of New Medicine Variants
5 | Discrepancies noted in MSME identification and Payment
6 | Discrepancies in timely adjustment of purchase returns and TDS during vendor payment
7 | Under-utilization of credit period | Pending in 24-25 Q4 follow-up
8 | Transaction logs in software systems
9 | Admission fee not charged for IP bills
10 | Discrepancies in Housekeeping Store Register
11 | Review of Fixed Asset Register | Pending in 24-25 Q4 follow-up
12 | Long outstanding creditors for capital goods | Pending in 24-25 Q4 follow-up
Apr-24-Dec-24 (From the ATR pending list of Q4 24-25 report)
1 | Long pending advance payments | Pending in 24-25 Q4 follow-up
2 | Vendor master data GST numbers and Mobile numbers not updated, no designated column for entering PAN, bank account number, IFSC code, MSME registration details, etc. | Pending in 24-25 Q4 follow-up
3 | Date of PO after bill date | Pending in 24-25 Q4 follow-up
4 | Suspense Account Reconciliation pending | Pending in 24-25 Q4 follow-up
5 | Inapproptiate Categorisation in stock reports | Pending in 24-25 Q4 follow-up
6 | Staff benefits and discount availment after resignation | Pending in 24-25 Q4 follow-up
75