Patient Experience Improvement Analysis

OP & IP Feedback Review, Waiting-Time Indicators, and Verbal Complaint Registers — December 2025 to June 2026

## Scope and Data Sources

This analysis covers 8,509 outpatient (OP) and 7,168 inpatient (IP) structured feedback responses collected through the hospital’s patient feedback forms over the six-month period December 2025 to June 2026 (June partial), together with 3,093 associated free-text comments, monthly verbal-complaint registers, the December 2025–February 2026 Feedback Management report, and HIS-based waiting-time indicators for diagnostics, OP consultation, and discharge spanning October 2025 to March 2026.

## Headline Metrics

| Metric | OP Services | IP Services |
| --- | --- | --- |
| Responses (6-month window) | 8,509 | 7,168 |
| Net Promoter Score | 87 | 36 |
| Promoters (score 9–10) | 90% | 49% |
| Detractors (score 1–6) | 3% | 13% |
| Average negative-rated share across service categories | 0.6% | 8.7% |

IP services trail OP services materially on both Net Promoter Score and category-level satisfaction, indicating that the inpatient pathway, rather than outpatient touchpoints, is the primary source of patient dissatisfaction across the review period.

## Top Issues Driving IP Detractor Scores

| Rank | Service Area | Negative Share | Responses Rated | Note |
| --- | --- | --- | --- | --- |
| 1 | Parking | 24.1% | 3,139 | Highest detractor driver |
| 2 | Food & Beverage | 14.6% | 5,986 | Top-2 verbal complaint category |
| 3 | Discharge Process | 12.2% | 3,585 | Cycle time 139–171 min |
| 4 | Maintenance / Engineering | 10.1% | 3,230 | Leading verbal complaint category |
| 5 | IP Billing | 9.0% | 3,296 | Linked to discharge delay |
| 6 | Direction Boards | 8.1% | 3,337 | Wayfinding in new block |
| 7 | Insurance Coordination | 7.6% | 4,118 | Claim/communication gaps |

## Core Issues Identified

Parking capacity and upkeep: comments cite insufficient space, uneven or unpaved surfacing, and an absence of extended-stay bystander provisions; this is the largest single driver of IP detractor scores and recurs in OP free-text comments.

Food & Beverage service: temperature, delivery timeliness, and quality dominate the feedback; verbal-complaint registers confirm F&B as a top-two department by complaint volume each month from December to February (74–108 complaints/month).

Discharge process delay: cash discharge cycle time ranges 139–171 minutes across the period; comments attribute delay to limited coordination between billing, pharmacy, and nursing, and to late return of admission documents.

Engineering and maintenance: air-conditioning faults and room-fixture upkeep form the leading verbal-complaint category in every month reviewed (51–91 complaints/month), with repeat complaints from the same rooms suggesting inconsistent ticket closure.

IP billing and insurance coordination: patients report unclear claim-exclusion communication, slow query turnaround, and limited staff awareness of the online payment portal, which compounds discharge delay.

OP waiting time: average consultation wait holds at 100–110 minutes for four of six months, easing to 88 minutes in March; lift access in the new block is repeatedly flagged in free-text comments.

Complaint closure cycle: 34 of 238 logged inpatient complaints remained open at the close of February 2026 (14% carryover), indicating room to tighten closure cycle time alongside the structural fixes above.

## Improvement Plan

| Focus Area | Action | Owner | Timeline |
| --- | --- | --- | --- |
| Parking | Re-surface and stripe patient/bystander parking; reserve bays for stays beyond 3 days; add signage and peak-hour security presence. | Facilities & Security | 0–60 days |
| Food & Beverage | Introduce insulated meal trolleys with a 30-minute kitchen-to-ward SLA; daily dietician tray audits; standardize hot/cold packaging. | F&B / Clinical Nutrition | 0–45 days |
| Discharge Process | Single-window discharge coordination across billing, pharmacy, and nursing; target cycle time under 90 minutes; root-cause review on cases exceeding 4 hours. | Nursing Ops, Billing, IT | 30–90 days |
| Maintenance | Preventive AC maintenance calendar; 24-hour ticket-closure SLA with escalation; pre-admission room-readiness checklist. | Engineering | 0–30 days |
| Billing & Insurance | Assign ward-level insurance coordinators; share pre-discharge bill estimates; train billing staff on the online payment portal. | Billing & Insurance | 30–60 days |
| OP Waiting Time | Enforce appointment slot adherence with digital queue display; assess added lift capacity or staggered scheduling in the new block. | OP Operations | 60–90 days |

Monitoring: track NPS and category-wise negative share monthly by service head; target complaint closure of 95% within 48 hours; review progress against this plan at Group COO level on a quarterly cycle.