Cost for phase 1 and 2 : Rs 15 Lakh

Phase 1: Internal financial controls diagnostic study

Objective:
To obtain an in-depth understanding of existing processes and internal financial controls, identify control design and implementation gaps and establish a clear baseline for remediation and improvement.

Phase 1 shall be executed as a diagnostic study, focusing on understanding the “as-is” environment rather than implementation.

Scope of activities:

(a) Process understanding and documentation

- Obtain an understanding of key end-to-end processes across the following domains:

  - Materials & stores

  - Human resources & payroll

  - Cost accounting & financial Accounting

  - Revenue & receivables

- Document process flows, key activities and existing control practices through discussions with process owners and review of relevant documentation.

(b) Internal financial controls assessment

- Identify key risks and “what can go wrong” scenarios relevant to financial reporting and operational integrity.

- Assess the adequacy, design and implementation of existing internal financial controls, including entity-level and process-level controls.

- Review maker-checker mechanisms, approval frameworks, segregation of duties and reconciliation controls embedded within processes.

(c) Risk control matrix (RCM) - review and development

- Review existing control documentation, if any, and develop / update RCMs for in-scope processes.

- Identify control gaps, redundancies and areas of control weakness, including reliance on manual or compensating controls.

(d) Diagnostic observations and prioritisation

- Identify gaps relating to inventory management, payroll and headcount controls, cost allocation, revenue recognition, receivables tracking and master data governance.

- Prioritise gaps based on risk, impact and ease of remediation.

Key deliverables – Phase 1:

- Diagnostic assessment report outlining current-state observations, control gaps and risks.

- Updated / newly developed RCMs for in-scope processes.

- High-level remediation roadmap identifying priority actions and phasing for subsequent stages.

Phase 2: IT and system-enabled controls review

Objective:
To assess the design and effectiveness of IT-dependent and system-enabled controls that support the internal financial controls environment.

This phase will be undertaken with support from the Firm’s IT audit specialists, working in conjunction with the core engagement team.

Scope of activities:

- Review of IT general controls (ITGC) relevant to financial and operational systems, including user access management, change management and audit trails.

- Assessment of application-level controls supporting key processes such as inventory management, billing, payroll and accounting.

- Review of controls relating to:

  - Maker-checker enforcement within systems

  - Audit trail availability and integrity

  - Restrictions on back-dated entries and postings

  - Reliability of system-generated reports used for reconciliations, ageing analysis and management reporting

- Identification of gaps in system configuration and control reliance.

Key deliverables – Phase 2:

- IT controls assessment report highlighting gaps and recommendations.

- Integration of IT-related control observations into the overall controls framework and remediation roadmap.

Phase 3: Operational remediation, data clean-up and controls strengthening

Objective:
To support management in remediation of identified gaps, strengthen operational controls, and improve data quality and governance.

Scope of activities:

- Support in implementation of agreed control improvements across Materials & Stores, HR, Cost Accounting, Revenue and Receivables.

- Assistance in cleansing, reclassification and validation of key master and transactional datasets across operational and financial domains.

- Support in refining policies, procedures and approval matrices to embed improved controls into day-to-day operations.

- Testing of operating effectiveness of selected key controls, on a sample basis, post-implementation.

- Development of a detailed implementation plan with ownership, timelines and milestones.

Key deliverables – Phase 3:

- Corrected and validated datasets, ready for adoption into operational systems (management responsibility).

- Finalised internal controls framework and RCMs.

- Detailed implementation and monitoring plan.

- Management presentation summarising improvements implemented and residual risks.